## Slide 1: Ventspils County Municipality
LLI-10 Introducing nature tourism for all UniGreen
The project is co-financed by the Interreg V-A Latvia - Lithuania Cross Border Cooperation Programme 2014–2020 www.latlit.eu

## Slide 2: Activities in 3rd period
The contract about the building of Nature trail beside the Usma lake was finally signed
Complete purchase procedure:
  Price survey was unsuccessful – proposed costs were more than 3 times bigger than the planned costs
  Purchase procedure ended successfully only after the 2nd round – due to high price of chosen materials they were changed to functionally the same but more cheaper materials
Planned costs: 24500 EUR
Real building costs: 43763,11 EUR

## Slide 3: Activities in 3rd period
Building contract signed on 28/09/2018
Works will be finished till 01/12/2018 (if the weather permits)
Visitor counter will be set up after building works will be finished
Planned changes in WP: to move the excess money from „Travel and accommodation“ to „Infrastructure and works“ in amount of approx. 550 EUR.

## Slide 6: Thank you! Usma Parish manager Gendrihs Skesters +371 29287631 usma@ventspilsnd.lv