## Budget summary
PARTNER PAYMENT CLAIM | [8 empty] | Programme instructions about eligibility of costs and general reporting instructions are available in the Programme Manual and Practical Guide for reporting. All project partners are instructed to follow programme website for possible changes in those instructions or reporting templates.
PARTNER IDENTIFICATION
Project acronym |  | XXXX
Name of project |  | Potential and competiveness of biomass as energy source in Central BSR
Partner number and name |  | XXXX
Milestone and reporting period |  | 3 | /10 | September | 2012 | - | December | 2012 |  | 2008
1. REPORTED COSTS IN BUDGET LINES
|  |  |  | Approved budget | Current period | Previously reported | Cumulative | Remaining
1. Office and rent costs |  |  |  | 1200 | 141.45 | 120.28 | 261.73 | 938.27
2. Personnel |  |  |  | 63802 | 11186.26 | 10651.88 | 21838.14 | 41963.86
| Personnel employed by the project |  |  | 63802 | 11186.26 | 10651.88 | 21838.14 | 41963.86
| Other partner personnel contributing to the project |  |  |  | 0 |  | 0 | 0
| Unpaid voluntary labour |  |  |  | 0 |  | 0 | 0
3. Travel and accommodation |  |  |  | 7094 | 1309.02 | 0 | 1309.02 | 5784.98
| Travel costs in the programme area |  |  | 7094 | 1309.02 |  | 1309.02 | 5784.98
| Travel costs outside the programme area |  |  |  | 0 |  | 0 | 0
4. External expertise |  |  |  | 23520 | 13511.07 | 0 | 13511.07 | 10008.93
| Expert services |  |  | 23520 | 13511.07 |  | 13511.07 | 10008.93
| Audit, First Level Control |  |  |  | 0 |  | 0 | 0
| Evaluations |  |  |  | 0 |  | 0 | 0
5. Equipment |  |  |  |  | 0 |  | 0 | 0
6. Investments |  |  |  |  | 0 |  | 0 | 0
7. Other direct costs |  |  |  | 10300 | 0 | 1732.14 | 1732.14 | 8567.86
8. In kind contributions |  |  |  |  | 0 |  | 0 | 0
9. Incomes |  |  |  |  | 0 |  | 0 | 0
TOTAL |  |  |  | 105916 | 26147.8 | 12504.3 | 38652.1 | 67263.9
2. REPORTED PARTNER FINANCING | [8 empty] | If an error message appears on this row, please check that the reported in kind contributions do not exceed the national funding for the milestone. If project partner has accumulated more in kind contributions that can be reported for the milestone, please fill in support document for in kind contributions.
|  |  |  | Approved budget | Current period | Previously reported | Cumulative | Remaining
PUBLIC FUNDING (TOTAL) |  |  |  | 105916 | 26147.8 | 12504.3 | 38652.1 | 67263.9
ERDF |  |  |  | 85792 | 21179.718 | 10128.49 | 31308.208 | 54483.792
NATIONAL PUBLIC FUNDING |  |  |  | 20124 | 4968.082 | 2375.81 | 7343.892 | 12780.108
NATIONAL PRIVATE FUNDING | [6 empty] | 0 | 0
TOTAL |  |  |  | 105916 | 26147.8 | 12504.3 | 38652.1 | 67263.9
Approved ERDF rate of partner |  |  |  | 81%
Reported ERDF rate of partner |  |  |  | 81%
3. SIGNATURE
Date and place |  |  |  | 15/01/2013 |  | Riga
|  |  |  | Date (dd/mm/yyyy) |  | Place
If an error messages appears in this row, please check that project costs and financing have been reported in equal amounts
Signature(s)
Name of the signatory |  |  |  | xxx
Position in the institution
Partner institution |  |  |  | zzzzz
Stamp of the Partner institution
4. SIGNATURE OF THE FIRST LEVEL CONTROLLER
Date and place
|  |  |  | Date (dd/mm/yyyy) |  | Place
Signature(s)
Name of the signatory
Position in the institution
Partner institution
Stamp of the National Controller (if available)

## Activity report
ACTIVITY REPORT | [14 empty] | yes
no
Project acronym |  | XXXX
Name of project |  | Potential and competiveness of biomass as energy source in Central BSR
Partner number and name |  | XXXX
Milestone and reporting period |  | 3 | /10 |  | September |  |  | 2012 |  | - |  | December | 2012
Table of contents:
A1. Work Package 1
A2. Work Package 2
A3. Work Package 3
A4. Work Package 4
A5. Work Package 5
A6. General information on project performance and results
A6.1. Contribution to general objectives and aims of the project
A6.2. Cross-border added value
A6.3. Communication and publicity
A1. Work Package 1 | [13 empty] | Table of contents
Title of WP1 | Project management and coordination
Responsible partner of WP1 | ZZZZZ
Involved partners in WP1 | All Partners
2014
Activities of the Milestone
Procurement procedures for external services - traveling services to WG and SG meetings in Turku (Finland) were organized . Procurement procedures were completed, contract signed and traveling services provided. Financial management of the activities were ensured. 2 WG meetings with Latvia partners were organized to discuss issues on implementation of activities Preparation of 2nd Progress report and Payment claim was made, but because of delay in receiving Control Reports for Latvia and Finland partners , the JTS prolonged date of submitting of PR/PC MS2 until 31 of January 2013.
Maximum number of characters in this input field is 3000.
Number of characters in input fields |  |  |  | 1. | 595 | 2 | 0 |  | 3. | 0
Outputs of the Milestone
1. Prepared procurement procedures for external services or equipment by project partners; 2. Ensured Financial management of the activities; 3. Prepared Progress report and Payment claim.
Maximum number of characters in this input field is 500.
Number of characters in input fields |  |  |  | 1. | 0
Deviations from the approved project application | [13 empty] | Table of contents
Have some of the plans of the application form not been fulfilled? | [10 empty] | no
If yes, provide information on why this has happened, how you do intend to rectify the situation and which lessons you have learned.
Maximum number of characters in this input field is 1000.
Number of characters in input fields |  |  |  | 1. | 0
A2. Work Package 2 | [13 empty] | Table of contents
Title of WP2 | Biomass potential assessment and mapping
Responsible partner of WP2 | Turku University of Applied Sciences
Involved partners in WP2 | All partners
Activities of the Milestone
n.a
Maximum number of characters in this input field is 3000.
Number of characters in input fields |  |  |  | 1. | 3 | 2 | 0 |  | 3. | 0
Outputs of the Milestone
n.a
Maximum number of characters in this input field is 500.
Number of characters in input fields |  |  |  | 1. | 0
Deviations from the approved project application | [13 empty] | Table of contents
Have some of the plans of the application form not been fulfilled?
If yes, provide information on why this has happened, how you do intend to rectify the situation and which lessons you have learned.
Maximum number of characters in this input field is 1000.
Number of characters in input fields |  |  |  | 1. | 0
A3. Work Package 3 | [13 empty] | Table of contents
Title of WP3 | Biomass supply – demand modeling, CBA and competence tools
Responsible partner of WP3 | Lead partner - Kurzeme Planning Region
Involved partners in WP3 | All partners
Activities of the Milestone
According to the elaborated technical specification and signed contract Studies on legal bases of biomass use in the state, regional and local levels (includes the studies on state laws and rules, local strategies and plans as well as on all kind of regulations) was completed. To LP was presented pilotproject results for Market analysis on supply and demand modeling of biomass (current situation and potential) implemented by PP4 VCC. Development of the calculation tool (methodology and guidelines) for determining the long, mid and short term financial, socio-economical and environmental benefits form the use of Biomass as energy source was made by PP3 TUAS and was presented during the WG/SG 2nd meetings in Turku.
Maximum number of characters in this input field is 3000.
Number of characters in input fields |  |  |  | 1. | 724 | 2 | 0 |  | 3. | 0
Outputs of the Milestone
1. Elaborated technical specification for the procurement procedure; 2. Completed research document on biomass use in partner countries; 3. Completed analysis on supply and demand modeling of biomass in partner countries; 4. Presented first results on 3rd activity – content of the methodology.
Maximum number of characters in this input field is 500.
Number of characters in input fields |  |  |  | 1. | 0
Deviations from the approved project application | [13 empty] | Table of contents
Have some of the plans of the application form not been fulfilled? | [10 empty] | no
If yes, provide information on why this has happened, how you do intend to rectify the situation and which lessons you have learned.
Maximum number of characters in this input field is 1000. | [13 empty] | Table of contents
Number of characters in input fields |  |  |  | 1. | 0
A4. Work Package 4
Title of WP4 | Promotion and Dissemination
Responsible partner of WP4 | City of Turku - Valonia
Involved partners in WP4 | All partners
Activities of the Milestone
Project communication plan was approved by JTS. LP ensured communication between project partners and JTS. Information about results of procurement process in project was inserted in homepage of KPR www.kurzemesregions.lv . General information about project, its objectives, partners and budget were prepared and will be sent to media after receiving of results of Cost – benefit analysis .
Maximum number of characters in this input field is 3000.
Number of characters in input fields |  |  |  | 1. | 394 | 2 | 0 |  | 3. | 0
Outputs of the Milestone
1. Prepared and distributed third press release (information on project activities); 4. Organized study trip to Stockholm and Upsala region;
Maximum number of characters in this input field is 500.
Number of characters in input fields |  |  |  | 1. | 0
Deviations from the approved project application | [13 empty] | Table of contents
Have some of the plans of the application form not been fulfilled? | [10 empty] | yes
If yes, provide information on why this has happened, how you do intend to rectify the situation and which lessons you have learned.
Deviations Because Study on legal base of biomass use and CBA of biomass use will be completed in MS4, was decided to prepare 2nd press release after completion of Studies (in April 2013).Because Study on legal base of biomass use and CBA of biomass use will be completed in MS4, was decided to prepare 2nd press release after completion of Studies (in April 2013). Because most appropriate time for visiting of algae biomass production is spring, during WG/SG meeting in Turku was decided to organize study trip to Sweden in MS4
Maximum number of characters in this input field is 1000.
Number of characters in input fields |  |  |  | 1. | 540
A5. Work Package 5 | [13 empty] | Table of contents
Title of WP5
Responsible partner of WP5
Involved partners in WP5
Activities of the Milestone
Maximum number of characters in this input field is 3000.
Number of characters in input fields |  |  |  | 1. | 0 | 2 | 0 |  | 3. | 0
Outputs of the Milestone
Maximum number of characters in this input field is 500.
Number of characters in input fields |  |  |  | 1. | 0
Deviations from the approved project application | [13 empty] | Table of contents
Have some of the plans of the application form not been fulfilled?
If yes, provide information on why this has happened, how you do intend to rectify the situation and which lessons you have learned.
Maximum number of characters in this input field is 1000.
Number of characters in input fields |  |  |  | 1. | 0
A6. General information on project performance and results | [13 empty] | Table of contents
A6.1. Contribution to general objectives and aims of the project
Please describe how the activities of the project period have contributed to the central objectives and aims of the project. Have you achieved what you expected? What changes have you had to make to the original plans?
In the MS3 were made all necessary organizational activities to continue implementation of the project – necessary project budget allocations according to partners request was made, external services in WP3 -Study on legal base of biomass use was accomplished according to signed contract . Planned Steering group meeting and work groups meetings were organized.
Maximum number of characters in this input field is 1000.
Number of characters in input fields |  |  |  | 1. | 367
A6.2. Cross-border added value | [13 empty] | Table of contents
How has the cross-border character been reflected in the reporting period? What has been the cross-border added value in the reporting period?
During this period project partners established contacts and already started experience exchange among them sharing their knowledge to the other project partners, thus increasing the competency on Biomass issues for all of the project partners.
Maximum number of characters in this input field is 1000.
Number of characters in input fields |  |  |  | 1. | 246
A6.3. Communication and publicity | [13 empty] | Table of contents
What activities have you taken to implement the communication plan during this reporting period? What were the outputs?
Project communication plan was approved by JTS. According to the communication plan there was information exchange and communication between project partners during WG and SG meetings, via e-mail and phone conversations during all period in process of implementation of activities and solving other issues concerning implementation process of the project as well as information dissemination to general public via homepages of partners and press releases. LP ensured communication between project partners and JTS.
Maximum number of characters in these input fields is 2000.
Number of characters in input fields |  |  |  | 1. | 517 | 2. | 0

## Specification of budget lines
SPECIFICATION OF BUDGET LINES
Project acronym |  |  | XXXX
Name of project |  |  | Potential and competiveness of biomass as energy source in Central BSR
Partner number and name |  |  | XXXX
Milestone and reporting period |  |  | 3 | /10 | September | 2012 | - | December | 2012
BUDGET LINE 1: OFFICE AND RENT COSTS | [13 empty] | WP1
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU | WP2
WP3
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ? |  |  | WP4 | WP1 | WP2 | WP3 | WP4 | WP5
48 | 080963 RKP | 23.11.2012. | 29.11.2012. | Stationery for project personnel |  |  |  | 54.09 | 11.36 | LVL | 0.6962 | 94.01 | no | WP5 | #REF! | #REF! | #REF! | #REF! | #REF!
26 | 63619323 | 01.09.2012. | 17.09.2012. | Telephone for project manager and accountant per August, 2012 |  |  |  | 3.86 | 0.81 | LVL | 0.6962 | 6.71 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
36 | 63832215 | 01.10.2012. | 17.10.2012. | Telephone for project manager and accountant per September, 2012 |  |  |  | 6.64 | 1.39 | LVL | 0.6962 | 11.53 | no | yes | #REF! | #REF! | #REF! | #REF! | #REF!
47 | 64042640 | 01.11.2012. | 20.11.2012. | Telephone for project manager and accountant per October, 2012 |  |  |  | 9.78 | 2.05 | LVL | 0.6962 | 16.99 | no | no | #REF! | #REF! | #REF! | #REF! | #REF!
55 | 64348258 | 01.12.2012. | 11.12.2012. | Telephone for project manager and accountant per November, 2012 |  |  |  | 7.03 | 1.47 | LVL | 0.6962 | 12.21 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Office and Rent costs" | [11 empty] | 141.45 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
BUDGET LINE 2: PERSONNEL
Internal no° | Payment Date | Month | Name of Employee | [5 empty] | Total amount | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[9 empty] | [nat. currency] |  | 1 EUR= ?
PERSONNEL EMPLOYED BY THE PROJECT | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
27, 30, 31 | 28.09.2012. | September | [6 empty] | 943.08 | LVL | 0.6962 | 1354.61 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
28, 30, 31 | 28.09.2012. | September | [6 empty] | 729.65 | LVL | 0.6962 | 1048.05 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
29, 30, 31 | 28.09.2012. | September | [6 empty] | 277.96 | LVL | 0.6962 | 399.25 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
42, 45, 46 | 31.10.2012. | October | [6 empty] | 1131.7 | LVL | 0.6962 | 1625.54 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
43, 45, 46 | 31.10.2012. | October | [6 empty] | 729.65 | LVL | 0.6962 | 1048.05 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
44, 45, 46 | 31.10.2012. | October | [6 empty] | 277.96 | LVL | 0.6962 | 399.25 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
50, 53, 54 | 30.11.2012. | November | [6 empty] | 972.87 | LVL | 0.6962 | 1397.4 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
51, 53, 54 | 30.11.2012. | November | [6 empty] | 759.43 | LVL | 0.6962 | 1090.82 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
52, 53, 54 | 30.11.2012. | November | [6 empty] | 277.96 | LVL | 0.6962 | 399.25 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
57, 60, 61 | 27.12.2012. | December | [6 empty] | 814.03 | LVL | 0.6962 | 1169.25 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
58, 60, 61 | 27.12.2012. | December | [6 empty] | 595.63 | LVL | 0.6962 | 855.54 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
59, 60, 61 | 27.12.2012. | December | [6 empty] | 277.96 | LVL | 0.6962 | 399.25 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Personnel employed by the project" | [11 empty] | 11186.26 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
OTHER PARTNER PERSONNEL CONTRIBUTING TO THE PROJECT | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Other partner personnel contributing to the project" | [11 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
UNPAID VOLUNTARY LABOUR | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Unpaid voluntary labour" | [11 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Personnel" | [11 empty] | 11186.26
BUDGET LINE 3: TRAVEL AND ACCOMMODATION
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ?
TRAVEL COSTS IN THE PROGRAMME AREA | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
19 | 1040474123 | 30.09.2012. | 20.08.2012. | Transportation costs for meeting 18.09.2012. (advance payment for fuel according to order Nr.8-7/CB56/03 is LVL 100.00) |  |  |  | 44.27 | 9.3 | LVL | 0.6962 | 76.95 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
35 | 5008036 | 15.10.2012. | 17.10.2012. | Airplane tickets and insurance for X and Y (travel to WG and SG meetings in Finnland,Turku) |  |  |  | 526.24 | 0 | LVL | 0.6962 | 755.87 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
37 |  | 12.10.2012. | 18.10.2012. | Accomodation in Turku (travel to WG and SG meetings in Finnland,Turku) |  |  |  | 150.4 |  | LVL | 0.6962 | 216.03 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
38 | 8-7/CB56/K-02 | 15.10.2012. | 24.10.2012. | Per diem (travel to WG and SG meetings in Finnland,Turku) - |  |  |  | 64 |  | LVL | 0.6962 | 91.93 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
39 | 8-7/CB56/K-03 | 15.10.2012. | 24.10.2012. | Per diem (travel to WG and SG meetings in Finnland,Turku) - |  |  |  | 64 |  | LVL | 0.6962 | 91.93 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
40 | 2/CB56 | 26.10.2012. | 15.11.2012. | Travel expenses (public transportation costs in Turku) - |  |  |  | 3.52 |  | LVL | 0.6962 | 5.06 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
41 | 1/CB56 | 26.10.2012. | 15.11.2012. | Travel expenses (public transportation costs in Turku) - |  |  |  | 3.52 |  | LVL | 0.6962 | 5.06 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
49 | 3/CB56 | 23.11.2012. | 29.11.2012. | Transportation costs for meeting (22.11.2012.) according to order Nr.8-7/CB56/K-04 |  |  |  | 1.55 | 0.33 | LVL | 0.6962 | 2.7 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
19 | 1040493038 | 30.11.2012. | 20.08.2012. | Transportation costs for meeting 22.11.2012. (advance payment for fuel according to order Nr.8-7/CB56/03 is LVL 100.00) |  |  |  | 36.53 | 7.67 | LVL | 0.6962 | 63.49 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Travel costs in the programme area" | [11 empty] | 1309.02 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
TRAVEL COSTS OUTSIDE THE PROGRAMME AREA | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Travel costs outside the programme area" | [11 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Travel and accommodation" | [11 empty] | 1309.02
BUDGET LINE 4: EXTERNAL EXPERTISE
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ?
EXPERT SERVICES | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
32, 33, 34 | 1 | 24.09.2012. | 02.10.2012. | Activity coordinator (WP3 act. 1. and 4.) |  |  |  | 1555.32 |  | LVL | 0.6962 | 2234.01 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
25 | 16/2012 | 05.09.2012. | 17.09.2012. | Advance payment for the study (Ekoncepti, Ltd) |  |  |  | 2168.5 | 455.39 | LVL | 0.6962 | 3768.87 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
56 | 25/2012 | 13.12.2012. | 19.12.2012. | Interim payment for the study (Ekoncepti, Ltd) |  |  |  | 4320 | 907.2 | LVL | 0.6962 | 7508.19 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Expert services" | [11 empty] | 13511.07 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
AUDIT, FIRST LEVEL CONTROL | [14 empty] | WP1 | WP2 | WP3 | WP4 | WP5
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | 0 | no |  | #REF! | #REF! | #REF! | #REF! | #REF!
Subtotal "Audit, First Level Control" | [11 empty] | 0 |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
EVALUATIONS
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
Subtotal "Evaluations" | [11 empty] | 0
Subtotal "External Expertise" | [11 empty] | 13511.07
BUDGET LINE 5: EQUIPMENT
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ?
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
Subtotal "Equipment" | [11 empty] | 0
BUDGET LINE 6: INVESTMENTS
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ?
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
Subtotal "Investments" | [11 empty] | 0
BUDGET LINE 7: OTHER DIRECT COSTS
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ?
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Subtotal "Other direct costs" | [11 empty] | 0
BUDGET LINE 8: IN KIND CONTRIBUTIONS
Internal no° | Invoice no° | Invoice date | Payment Date | Specification of the invoice |  |  |  | Eligible net amount | Eligible VAT | Nat. Currency | Exchange Rate | Total amount paid | Outside EU
[8 empty] | [nat. currency] | [nat. currency] |  | 1 EUR= ?
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
Subtotal "In kind contributions" | [11 empty] | 0
BUDGET LINE 9: INCOME
Internal no° | Date | Specification of the invoice | [6 empty] | Amount | Nat. Currency | Exchange Rate | Total amount in EUR | Outside EU
[9 empty] | [nat. currency] |  | 1 EUR= ?
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
[12 empty] | 0 | no
Subtotal "Income" | [11 empty] | 0