## Slide 1: WP Management Alise Lūse Project Manager
CB786 Nature access to all NatAc
The project is co-financed by the Central Baltic Programme 2014–2020 www.centralbaltic.eu

## Slide 2: Project Coordination Group
Partners
P2 – NGO West-Estonia Tourism: Sille Roomets
Lead Partner
Kurzeme Planning Region – Alise Lūse
P3 – Metsähallitus: Laura Lehtonen
P4 – Keskkonnaamet: Margit Turb

## Slide 3: Project Steering Group
Partners and NGOs
P2 - NGO West-Estonia Tourism: tbc
Lead Partner
Kurzeme Planning Region: Aiga Petkēvica, Head of Project Division
P4 – Keskkonnaamet: Maris Kivistik
NGO Latvia: Apeirons, Raitis Briedis
NGO Estonia: Estonian Chamber of Disabled People, Meelis Joost
P3 - Metsähallitus: Hanna Ylitalo
NGO Finland: tbc

## Slide 4: Subsidy Contract, Partnership Agreements, other agreements
Subsidy Contract
MA to Lead Partner
Partnership Agreements
Lead Partner to Partners
Agreement with Apeirons on Mapeirons
All Partners

## Slide 5: Meetings
1 delegate to Project Coordination Group
1 delegate to Project Steering Group
Kick-off in Kurzeme 05.19.
PMM1 meeting in Estonia 10.19.
PMM2 meeting in Finland 05.20.
PMM3 meeting in Estonia 10.20.
PMM4 meeting in Kurzeme 01.21.
01.05.19.-31.10.19.
01.11.19.-30.04.20.
01.11.20.-30.04.21.
01.05.20.-31.10.20.
M.1.1.

## Slide 6: Reporting
Partners reports
Consolidated reports (LP)
Partner Report 0
during the first months of project implementation
Partner Reports 1 – 4
15 days after the end of the reporting period
Project Reports 1 – 4
in 4 months after the end of the reporting period
01.05.19.-31.10.19.
01.11.19.-30.04.20.
01.11.20.-30.04.21.
01.05.20.-31.10.20.
ems.centralbaltic.eu
Finland should contract an external auditor
Notes: + Info on Ems on Procurements above the national thresholds

## Slide 7: Payments
Partner Report submitted
15 days after the end of the period
FLC check
3 months
Project Report
4 months after the end of the period
60% advance of certified ERDF
JS check
90 days
Final payment
7 months
⓪ = first months of project implementation
① = 03.20. 60% payment ERDF to Lead Partner; 06.20. >40% payment ERDF to Lead Partner
②③④ = max 4 months 60%; max 7 months >40%

## Slide 8: Infrastructure improvements Lead Partner

## Slide 9: Infrastructure improvements Lead Partner
Deliverable No. | Deliverable title | Target value | Delivery date
I1.1.1 | Alsunga municipality, Žibgrava trail (dry closet, benches, wooden boardwalk, small bridges, reconstruction of a trail stretch) | 1 | Period 4
I1.1.2 | Aizpute municipality, Kazdanga Park and Kazdanga Castle Park (2 dry closets, ramp, benches, reconstruction of trail stretches) | 1 | Period 4
I1.1.3 | Ventspils municipality, Lake Būšnieku Trail (dry closet, installation of edges on the wooden boardwalk, benches) | 1 | Period 1
I1.1.4 | Liepāja, Horse Island Trail (dry closet, trail stretch to it, accessibility improvements at parking lot) | 1 | Period 2
I1.1.5 | Skrunda municipality, trail along the River Venta (dry closet, trail stretch to it) | 1 | Period 1
I1.1.6 | Priekule municipality, Kalētu Forest park (dry closet, resting area, ramp, tables, benches, reconstruction of trail stretches and a small bridge) | 1 | Period 4

## Slide 10: Infrastructure improvements Lead Partner – Liepāja Horse island

## Slide 11: Infrastructure improvements Lead Partner – Ventspils, Lake Būšnieku trail

## Slide 12: Infrastructure improvements Lead Partner – Skrunda, trail along the River Venta

## Slide 13: Infrastructure improvements Lead Partner – Alsunga, Žibgrava trail

## Slide 14: Infrastructure improvements Lead Partner – Kazdanga park

## Slide 15: Infrastructure improvements Lead Partner – Kazdanga Castle park

## Slide 16: Infrastructure improvements Lead Partner – Priekule, Kalēti Forest Park

## Slide 17: Joint Product Development
Development of accessibility CL
Development of joint materials
Learning best practise
Developing chain of accessible sites

## Slide 18: Joint Materials
Signs and info boards
Responsible partner for development: Metsähallitus
Production: LP, PP2, PP3
16
Period 3

## Slide 19: Joint Materials
QR codes with audio and video
Responsible partners: LP, PP2, PP3
16
Period 3

## Slide 20: Joint Materials
Tactile & Braille info stands
16
Period 2
Responsible partners: LP, PP2, PP3

## Slide 21: Joint Materials
Tactile objects
16
Period 3
Responsible partners: LP, PP2, PP3

## Slide 22: Joint Materials
Tactile objects
16
Period 3
Responsible partners: LP, PP2, PP3

## Slide 23: Joint Materials
Senses focused toolboxes
15
Period 3
Responsible partner: PP4

## Slide 24: Learning best practise
Experience exchange visit to Denmark
32
Period 1
Responsible partner: PP4
Partners, municipality & tourism specialists, NGOs
Focus on the nature visitors centres and organisations that deal with outdoor accessibility issues to learn from best examples on accessible nature sites and on development of materials for disabled people, accessibility branding and information channelling. Visits to accessible sites.

## Slide 25: Accessibility Check-list
Development of the CL
3
Period 1
Responsible partner: LP
In cooperation with NGOs
Thematic workshops
Period 2
1
LV, EE, FI
for municipalities, visitor centres, local operators etc. on developing accessible tourism products, use of self-testing tool, efficient accessibility solutions (total 150 participants)

## Slide 26: Development of the chain of accessible nature sites
On-spot inspection visits
at project sites
Period 1: 16
Responsible partner: LP, PP2, PP3
48
Period 2: 11
Period 3: 11
Period 4: 10
On-spot inspection visits
at other sites
35 round visits
Period 1: 17
Period 3: 18
To agree on inspection criteria for trails – type, length, hiking time, marking, trail surface, difficulty, accessibility level, facilities, rules to follow etc.
2) Trail passports
3) Recording GPX

## Slide 27: Marketing&Promotion
Marketing activities
Public events&promotional materials

## Slide 28: Public events&promotion
FAM workshops for messengers
3
LV, EE, FI
Period 2
How to access and spread info on accessible destinations among the target group. Total no of participants - 20.
Responsible partner: LP, PP2, PP3
Participation at Europarc Conference 2020
1
In Latvia – Ķemeri National Park
Responsible partner: PP4
Period 3
workshop on accessibility challenges and achievements by project partners (PP3 covers costs from own resources)

## Slide 29: Public events&promotion
FAM workshops with GER, UK, SE, USA, Asia tour operators
5
09.2019 - 02.2020
Period 2
to market the CB core area in LV, EE nad FI as a single accessible nature tourism destination
Responsible partner: PP2
FAM workshops
3
LV, EE, FI
Responsible partner: LP, PP, PP3
Period 3
Accessibility Days for families with disabilities to meet and visit the improved project sites. Total no of participants - 90.

## Slide 30: Public events&promotion
Tactile and Braille info cards & flyers for project sites
16
Period 4
Responsible partner: LP, PP2, PP3

## Slide 31: Marketing
Mobile-friendly internet platfom
Period 3
Responsible partner: LP

## Slide 32: Marketing
Travel Guide on accessible sites
Period 4
Responsible partner: LP, PP2, PP3
16000
LV, EE, FI, ENG

## Slide 33: Marketing
Publishing on other sites & apps
Period 4
Responsible partner: all partners
15
PP2 site adapted to visually impaired
visitkurzeme.lv, kurzemesregions.lv, latvia.travel
westestonia.com, visitestonia.com,
metsa.fi, nationalparks.fi

## Slide 34: Communication
Project Poster

## Slide 35: Communication
https://www.kurzemesregions.lv/en/projects/tourism/natac/
Website section

## Slide 36: Communication
Facebook posts - 50
Website updates - 40
Period 1 - 8, in Period 2 - 10, in Period 3 - 16, in Period 4 - 16
Period 1 - 8, in Period 2 - 10, in Period 3 - 11, in Period 4 - 11
Articles - 3
Period 1 - 1, in Period 3 - 1, in Period 4 - 1

## Slide 37: Communication
Final conference in Kurzeme – 100 participants

## Slide 38: Period 1

## Slide 39: Period 1
Infastructure development activities
LP – at Skrunda and Ventspils
West-Estonia – at Haapsalu, Lääne-Nigula and Lääneranna
Joint Product Development
LP – Accessibility CL
All partners – Study visit to Denmark
All partners – on-site inspection visits at project sites and outside
Communication
LP - article
All partners – website section + updates + FB posts