## Slide 1: Pp 6: Kaunas regional development agency
Project No LLI-303
„Life in Clean Environment – a Better Future“
Project partners‘ meeting, Jurkalne, September 11, 2019

## Slide 2: Activities implemented during period 2 (1)
Work package M (Managmenet):
  Day-to-day management, planning and coordination.
  Communication with Lead Partner and Lithuanian partners.
  Report 2 prepared.
  PMG meeting organised in Telšiai on March 6, 2019

## Slide 3: Activities implemented during period 2 (2)
Work package T1 (Implementation):
  Thematic workshop in Telšiai on March 7, 2019 – 26 participants
  Roundtable discussion in Telšiai on November 11, 2018 – 21 participant
  Participation in seminar in Liepaja on April 24, 2019 – indirect project outcome – use of knowledge from the seminar - prepared and submitted ESPON application

## Slide 4: Activities implemented during period 2 (3)
Work package C (Communication)
  Information about the project and first events published on KRDA web-page and Facebook profile.
  Project poster is displayed in KRDA office and used during events.

## Slide 5: Activities planned
1 article about project results.
2 roundtable discussions:
  Gargždai (Period 2) will be moved to Period 4
  Kaunas (Period 3) planned in October
  Participants – local stakeholders, Lithuanian partners.
Experience exchange visit to Latvia:
  Period 4. 12 participants from Lithuania. 2 days (1 night).
  KRDA is responsible for the development of content, rent of bus, accommodation and catering of Lithuanian participants.
1 project management group meeting (PMG):
  PMM4 in Kaunas (Period 4), 2-3 persons from each partner. 1 day.
Final conference:
  Kaunas (Period 4), together with PMM4. 2-5 participants from each partner. 1,5 days event (1 night)

## Slide 6: Issues for the discussion
Experience exchange visits to Latvia and Lithuania:
  When?
  Content?
Seminars
  Who?
  When?
  Content?
Final conference:
  When?
  Content?

## Slide 7: Thank you for your attention!
Elena Taločkaitė
Kaunas Regional Development Agency
Project Manager
elena@krda.lt, +370 616 56771